## Scheme data
Version 3: Oct 20 |  | Input |  |  |  | Output | [11 empty] | OGP2020
Scheme name:
| Ref: | [5 empty] | Desired RCF Values: |  |  | RCF50 | %age Contingency: | 0% | RCF75 | %age Contingency: | 0% | Mean: (3) | 0%
[10 empty] | Choose RCFxx |  |  | Choose RCFxx
| Total budget (£): (note 1) |  |  |  |  | <=£1Bn | Pvalue | RCF (P) | RCF
| Development Stage: |  | GRIP Stage | or |  | ?? | P0 | 0%
[7 empty] | P5 | 5% | 0%
| Scheme Composition | Est £ | or %age |  | Calculated |  | P10 | 10% | 0%
| Land/ property |  |  |  | 0 |  | P15 | 15% | 0%
| New station(s) build (note 2) |  |  |  | 0 |  | P20 | 20% | 0%
| Refurbished station(s) work (Note 2) |  |  |  | 0 |  | P25 | 25% | 0%
| New track |  |  |  | 0 |  | P30 | 30% | 0%
| Track upgrade |  |  |  | 0 |  | P35 | 35% | 0%
| Electrification |  |  |  | 0 |  | P40 | 40% | 0%
| Signalling/ testing (new) |  |  |  | 0 |  | P45 | 45% | 0%
| Signalling/ testing (upgrade) |  |  |  | 0 |  | P50 | 50% | 0%
| Civils (embankments/ cuttings/ road works) |  |  |  | 0 |  | P55 | 55% | 0%
| Utility works |  |  |  | 0 |  | P60 | 60% | 0%
| Tunnels |  |  |  | 0 |  | P65 | 65% | 0%
| Bridges/ viaducts |  |  |  | 0 |  | P70 | 70% | 0%
| Temporary works |  |  |  | 0 |  | P75 | 75% | 0%
| Other buildings (depots etc) |  |  |  | 0 |  | P80 | 80% | 0%
| IT (hardware/ software) |  |  |  | 0 |  | P85 | 85% | 0%
| PM/ Design/ Prelims etc |  |  |  | 0 |  | P90 | 90% | 0%
| Total | 0 | 0% |  | 0% |  | P95 | 95% | 0%
[7 empty] | P100 | 100%
Project notes
[7 empty] | RCF Modelling Notes |  |  |  |  | Version 3: Oct 20
1. Analysis of data illustrates that budgets > or < £1Bn has no significant difference on the RCF.
2. Enhanced station data now included. Refurbished stations are considered same risk as new stations
This cost heading is for the station 'shell' only. Any 'signature' architectural statements would be higher risk.
Advise on this or any other unusual features in "notes"
3. Mean is arithmetic average.
Schedule Information
| Timenow: | 2020-11-01 |  |  |  |  | Desired RCF Values: |  |  | RCF50 | %age float: | #DIV/0! | RCF75 | %age float: | #DIV/0! | Mean: (3) | #DIV/0!
| Key Dates | [8 empty] | Choose RCFxx |  |  | Choose RCFxx
| Design start: (GRIP 4 start or equivalent): |  | Enter dates |  |  |  | Pvalue | RCF (P) | RCF
Delivery start: (GRIP 6 start or equivalent):
| Delivery end: (GRIP 6 end or equivalent): | [5 empty] | P0 | 0%
[7 empty] | P5 | 5% | #DIV/0!
| Durations: | Months |  |  |  |  | P10 | 10% | #DIV/0!
|  | Full duration | Rem. Duration |  |  |  | P15 | 15% | #DIV/0!
| Design to completion (e.g. GRIP 4 to end 6) | 0 | -1451.0466 | Calculated |  |  | P20 | 20% | #DIV/0!
| Delivery period (e.g. GRIP 6 start to finish): | 0 | -1451.0466 |  |  |  | P25 | 25% | #DIV/0!
[7 empty] | P30 | 30% | #DIV/0!
| The desired float (determined by risk appetite) can be either added to the cited durations or plan durations should allow this much float prior to the cited end date. I.e: | [5 empty] | P35 | 35% | #DIV/0!
[7 empty] | P40 | 40% | #DIV/0!
[7 empty] | P45 | 45% | #DIV/0!
[7 empty] | P50 | 50% | #DIV/0!
| Risk Appetite: | RCF75 | Choose RCFxx |  |  |  | P55 | 55% | #DIV/0!
| Effect on total duration (design to completion): | [5 empty] | P60 | 60% | #DIV/0!
| Either: | [5 empty] | P65 | 65% | #DIV/0!
| Add float to total duration of: |  | Months |  |  |  | P70 | 70% | #DIV/0!
| Giving a forecast end date of: | [5 empty] | P75 | 75% | #DIV/0!
| Or | [5 empty] | P80 | 80% | #DIV/0!
| Add float into duration of: |  | Months |  |  |  | P85 | 85% | #DIV/0!
| Giving a target: | [5 empty] | P90 | 90% | #DIV/0!
| Duration of: | [5 empty] | P95 | 95% | #DIV/0!
| and completion date of: | [5 empty] | P100 | 100%

## Calculated Cost RCF (hidden)
This sheet collates the relevant RCF data (cost) | [5 empty] | Scheme: | 0
Selector | ??<=£1Bn |  |  |  | %ages: | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Compound: Scheme Specific RCF | P50 | P75 | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc
| P0 | 0% |  | 0% | 0%
| P5 | 5% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P10 | 10% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P15 | 15% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P20 | 20% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P25 | 25% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P30 | 30% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P35 | 35% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P40 | 40% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P45 | 45% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P50 | 50% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P55 | 55% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P60 | 60% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P65 | 65% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P70 | 70% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P75 | 75% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P80 | 80% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P85 | 85% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P90 | 90% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P95 | 95% | 0% | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P100 | 100% |  | 0% | 0%
|  | Mean: | 0%

## Calculated Schedule RCF (hidden)
This sheet collates the relevant RCF data (cost) | [5 empty] | Scheme: | 0
Selector | ??<=£1Bn |  |  |  | %ages: | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | Recalc to exclude L&P: | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Compound: Scheme Specific RCF | P50 | P75 | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc
| P0 | 0% |  | #DIV/0! | #DIV/0!
| P5 | 5% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P10 | 10% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P15 | 15% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P20 | 20% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P25 | 25% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P30 | 30% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P35 | 35% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P40 | 40% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P45 | 45% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P50 | 50% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P55 | 55% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P60 | 60% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P65 | 65% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P70 | 70% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P75 | 75% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P80 | 80% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P85 | 85% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P90 | 90% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P95 | 95% | #DIV/0! | #DIV/0! | #DIV/0! | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| P100 | 100% |  | #DIV/0! | #DIV/0!
|  | Mean: | #DIV/0!
|  |  | Risk Appetite calc: | P75 | #DIV/0!

## RCF data (hidden)
|  |  | SOBC | [15 empty] | SOBC<1Bn | [15 empty] | OBC | [15 empty] | OBC <=£1Bn | [15 empty] | FBC | [15 empty] | FBC <=£1Bn | [15 empty] | CCT | [15 empty] | CCT <=£1Bn
| RCF Values |  | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc | Land & Property | New station(s) | Refurbished station(s) | New track | Track upgrade | Electrification | Signalling/ testing (new) | Signalling/ testing (upgrade) | Civils (embankments/ cuttings/ road works) | Utilities | Tunnels | Bridges/ viaducts | Temporary works | Other buildings (depots etc) | IT | PM/ Design/ Prelims etc
Cost RCF
| Notes |  |  | New data 12 Oct 20 | Stations x 1 |  | New x 1.1 |  |  | New x 1.1 | [8 empty] | As >1Bn | [16 empty] | New data 12 Oct 20 | Stations x 1 | [13 empty] | As >1Bn | [16 empty] | New data 12 Oct 20 | Stations x 1 | [13 empty] | As >1Bn | [16 empty] | Use buildings | Use Bldgs x 75% | [14 empty] | Use buildings | Use Bldgs x 75%
| P0 | 0%
| P5 | 5% | -92.48% | -17.2% | -17.2% | -29.15% | -29.15% | -38.51% | -73.57% | -73.57% | -31.82% | -42.09% | -30.82% | -27.68% | -27.65% | -27.65% | -73.57% | -30.82% | -92.48% | -17.2% | -17.2% | -29.15% | -29.15% | -38.51% | -73.57% | -73.57% | -31.82% | -42.09% | -30.82% | -27.68% | -27.65% | -27.65% | -73.57% | -30.82% | -94.04% | -17.2% | -17.2% | -29.15% | -29.15% | -38.51% | -69.88% | -69.88% | -31.82% | -42.09% | -30.82% | -27.68% | -27.65% | -27.65% | -69.88% | -30.82% | -94.04% | -17.2% | -17.2% | -29.15% | -29.15% | -38.51% | -69.88% | -69.88% | -31.82% | -42.09% | -30.82% | -27.68% | -27.65% | -27.65% | -69.88% | -30.82% | -95.6% | -7.377% | -7.377% | -19.33% | -19.33% | -28.69% | -63.74% | -63.74% | -22% | -32.26% | -21% | -17.85% | -17.83% | -17.83% | -63.74% | -21% | -95.6% | -7.377% | -7.377% | -19.33% | -19.33% | -28.69% | -63.74% | -63.74% | -22% | -32.26% | -21% | -17.85% | -17.83% | -17.83% | -63.74% | -21%
| P10 | 10% | -86.95% | -16.35% | -16.35% | -19.54% | -19.54% | -25.91% | -57.04% | -57.04% | -22.26% | -38.74% | -21.82% | -21.98% | -20.42% | -20.42% | -57.04% | -20.82% | -86.95% | -16.35% | -16.35% | -19.54% | -19.54% | -25.91% | -57.04% | -57.04% | -22.26% | -38.74% | -21.82% | -21.98% | -20.42% | -20.42% | -57.04% | -20.82% | -88.3% | -16.35% | -16.35% | -19.54% | -19.54% | -25.91% | -49.97% | -49.97% | -22.26% | -38.74% | -21.82% | -21.98% | -20.42% | -20.42% | -49.97% | -20.82% | -88.3% | -16.35% | -16.35% | -19.54% | -19.54% | -25.91% | -49.97% | -49.97% | -22.26% | -38.74% | -21.82% | -21.98% | -20.42% | -20.42% | -49.97% | -20.82% | -89.64% | -6.522% | -6.522% | -9.72% | -9.72% | -16.09% | -47.22% | -47.22% | -12.43% | -28.91% | -12% | -12.16% | -10.6% | -10.6% | -47.22% | -11% | -89.64% | -6.522% | -6.522% | -9.72% | -9.72% | -16.09% | -47.22% | -47.22% | -12.43% | -28.91% | -12% | -12.16% | -10.6% | -10.6% | -47.22% | -11%
| P15 | 15% | -72.36% | -10.49% | -10.49% | -10.77% | -10.77% | -13.24% | -39.48% | -39.48% | -12.63% | -28.95% | -13.43% | -15.83% | -10.12% | -10.12% | -39.48% | -11.83% | -72.36% | -10.49% | -10.49% | -10.77% | -10.77% | -13.24% | -39.48% | -39.48% | -12.63% | -28.95% | -13.43% | -15.83% | -10.12% | -10.12% | -39.48% | -11.83% | -71.91% | -10.49% | -10.49% | -10.77% | -10.77% | -13.24% | -34.26% | -34.26% | -12.63% | -28.95% | -13.43% | -15.83% | -10.12% | -10.12% | -34.26% | -11.83% | -71.91% | -10.49% | -10.49% | -10.77% | -10.77% | -13.24% | -34.26% | -34.26% | -12.63% | -28.95% | -13.43% | -15.83% | -10.12% | -10.12% | -34.26% | -11.83% | -71.46% | -4.663% | -4.663% | -4.942% | -4.942% | -7.42% | -33.66% | -33.66% | -6.803% | -23.13% | -7.601% | -10% | -4.291% | -4.291% | -33.66% | -6% | -71.46% | -4.663% | -4.663% | -4.942% | -4.942% | -7.42% | -33.66% | -33.66% | -6.803% | -23.13% | -7.601% | -10% | -4.291% | -4.291% | -33.66% | -6%
| P20 | 20% | -60.84% | -8.659% | -8.659% | -7.745% | -7.745% | -11.31% | -31.58% | -31.58% | -8.745% | -23.66% | -7.745% | -12.74% | -7.094% | -7.094% | -31.58% | -7.745% | -60.84% | -8.659% | -8.659% | -7.745% | -7.745% | -11.31% | -31.58% | -31.58% | -8.745% | -23.66% | -7.745% | -12.74% | -7.094% | -7.094% | -31.58% | -7.745% | -50.18% | -4.869% | -4.869% | -3.955% | -3.955% | -7.523% | -24.84% | -24.84% | -4.955% | -19.87% | -3.955% | -8.955% | -3.305% | -3.305% | -24.84% | -3.955% | -50.18% | -4.869% | -4.869% | -3.955% | -3.955% | -7.523% | -24.84% | -24.84% | -4.955% | -19.87% | -3.955% | -8.955% | -3.305% | -3.305% | -24.84% | -3.955% | -39.51% | -1.914% | -1.914% | -1% | -1% | -4.568% | -24.84% | -24.84% | -2% | -16.92% | -1% | -6% | -0.3492% | -0.3493% | -24.84% | -1% | -39.51% | -1.914% | -1.914% | -1% | -1% | -4.568% | -24.84% | -24.84% | -2% | -16.92% | -1% | -6% | -0.3492% | -0.3493% | -24.84% | -1%
| P25 | 25% | -43.73% | -1.207% | -1.207% | -2.73% | -2.73% | -5.57% | -19.93% | -19.93% | -2.73% | -6.144% | -1.73% | -5.98% | -2.73% | -2.73% | -19.93% | -1.73% | -43.73% | -1.207% | -1.207% | -2.73% | -2.73% | -5.57% | -19.93% | -19.93% | -2.73% | -6.144% | -1.73% | -5.98% | -2.73% | -2.73% | -19.93% | -1.73% | -31.17% | 1.523% | 1.523% | 0% | 0% | -2.84% | -17.2% | -17.2% | 0.0004427% | -3.414% | 1% | -3.25% | 0% | 0% | -17.2% | 1% | -31.17% | 1.523% | 1.523% | 0% | 0% | -2.84% | -17.2% | -17.2% | 0.0004427% | -3.414% | 1% | -3.25% | 0% | 0% | -17.2% | 1% | -18.6% | 1.523% | 1.523% | 0% | 0% | -2.84% | -17.2% | -17.2% | 0.0004427% | -3.414% | 1% | -3.25% | 0% | 0% | -17.2% | 1% | -18.6% | 1.523% | 1.523% | 0% | 0% | -2.84% | -17.2% | -17.2% | 0.0004427% | -3.414% | 1% | -3.25% | 0% | 0% | -17.2% | 1%
| P30 | 30% | -39.84% | 6.25% | 6.25% | 3.04% | 3.344% | -0.756% | -11.83% | -11.83% | 3% | 1.305% | 7.091% | -1% | 1.4% | 1.4% | -11.83% | 4% | -39.84% | 6.25% | 6.25% | 3.04% | 3.344% | -0.756% | -11.83% | -11.83% | 3% | 1.305% | 7.091% | -1% | 1.4% | 1.4% | -11.83% | 4% | -28.59% | 6.25% | 6.25% | 3.04% | 3.344% | -0.756% | -11.83% | -11.83% | 3% | 1.305% | 7.091% | -1% | 1.4% | 1.4% | -11.83% | 4% | -28.59% | 6.25% | 6.25% | 3.04% | 3.344% | -0.756% | -11.83% | -11.83% | 3% | 1.305% | 7.091% | -1% | 1.4% | 1.4% | -11.83% | 4% | -17.35% | 6.25% | 6.25% | 3.04% | 3.344% | -0.756% | -11.83% | -11.83% | 3% | 1.305% | 7.091% | -1% | 1.4% | 1.4% | -11.83% | 4% | -17.35% | 6.25% | 6.25% | 3.04% | 3.344% | -0.756% | -11.83% | -11.83% | 3% | 1.305% | 7.091% | -1% | 1.4% | 1.4% | -11.83% | 4%
| P35 | 35% | -24.74% | 11% | 11% | 6% | 6.6% | 0% | -7.427% | -7.427% | 6% | 1.439% | 11.78% | 0% | 3.966% | 3.966% | -7.427% | 7.07% | -24.74% | 11% | 11% | 6% | 6.6% | 0% | -7.427% | -7.427% | 6% | 1.439% | 11.78% | 0% | 3.966% | 3.966% | -7.427% | 7.07% | -17.33% | 11% | 11% | 6% | 6.6% | 0% | -7.427% | -7.427% | 6% | 1.439% | 11.78% | 0% | 3.966% | 3.966% | -7.427% | 7.07% | -17.33% | 11% | 11% | 6% | 6.6% | 0% | -7.427% | -7.427% | 6% | 1.439% | 11.78% | 0% | 3.966% | 3.966% | -7.427% | 7.07% | -9.913% | 11% | 11% | 6% | 6.6% | 0% | -7.427% | -7.427% | 6% | 1.439% | 11.78% | 0% | 3.966% | 3.966% | -7.427% | 7.07% | -9.913% | 11% | 11% | 6% | 6.6% | 0% | -7.427% | -7.427% | 6% | 1.439% | 11.78% | 0% | 3.966% | 3.966% | -7.427% | 7.07%
| P40 | 40% | -15.52% | 18% | 18% | 9.01% | 9.911% | 0% | -5% | -5% | 9% | 3.035% | 18% | 1.626% | 9% | 9% | -5% | 11% | -15.52% | 18% | 18% | 9.01% | 9.911% | 0% | -5% | -5% | 9% | 3.035% | 18% | 1.626% | 9% | 9% | -5% | 11% | -10.7% | 18% | 18% | 9.01% | 9.911% | 0% | -5% | -5% | 9% | 3.035% | 18% | 1.626% | 9% | 9% | -5% | 11% | -10.7% | 18% | 18% | 9.01% | 9.911% | 0% | -5% | -5% | 9% | 3.035% | 18% | 1.626% | 9% | 9% | -5% | 11% | -5.88% | 18% | 18% | 9.01% | 9.911% | 0% | -5% | -5% | 9% | 3.035% | 18% | 1.626% | 9% | 9% | -5% | 11% | -5.88% | 18% | 18% | 9.01% | 9.911% | 0% | -5% | -5% | 9% | 3.035% | 18% | 1.626% | 9% | 9% | -5% | 11%
| P45 | 45% | -10.09% | 25.72% | 25.72% | 13.07% | 14.37% | 0% | -2.08% | -2.288% | 13% | 5.995% | 23% | 6% | 12% | 12% | -2.08% | 14% | -10.09% | 25.72% | 25.72% | 13.07% | 14.37% | 0% | -2.08% | -2.288% | 13% | 5.995% | 23% | 6% | 12% | 12% | -2.08% | 14% | -7.342% | 25.72% | 25.72% | 13.07% | 14.37% | 0% | -2.08% | -2.288% | 13% | 5.995% | 23% | 6% | 12% | 12% | -2.08% | 14% | -7.342% | 25.72% | 25.72% | 13.07% | 14.37% | 0% | -2.08% | -2.288% | 13% | 5.995% | 23% | 6% | 12% | 12% | -2.08% | 14% | -4.59% | 25.72% | 25.72% | 13.07% | 14.37% | 0% | -2.08% | -2.288% | 13% | 5.995% | 23% | 6% | 12% | 12% | -2.08% | 14% | -4.59% | 25.72% | 25.72% | 13.07% | 14.37% | 0% | -2.08% | -2.288% | 13% | 5.995% | 23% | 6% | 12% | 12% | -2.08% | 14%
| P50 | 50% | 3.423% | 29.34% | 29.34% | 19% | 20.9% | 0% | 0% | 0% | 16% | 8.082% | 25.36% | 12% | 13.33% | 13.33% | 0% | 18% | 3.423% | 29.34% | 29.34% | 19% | 20.9% | 0% | 0% | 0% | 16% | 8.082% | 25.36% | 12% | 13.33% | 13.33% | 0% | 18% | -0.03982% | 29.34% | 29.34% | 19% | 20.9% | 0% | 0% | 0% | 16% | 8.082% | 25.36% | 12% | 13.33% | 13.33% | 0% | 18% | -0.03982% | 29.34% | 29.34% | 19% | 20.9% | 0% | 0% | 0% | 16% | 8.082% | 25.36% | 12% | 13.33% | 13.33% | 0% | 18% | -3.503% | 29.34% | 29.34% | 19% | 20.9% | 0% | 0% | 0% | 16% | 8.082% | 25.36% | 12% | 13.33% | 13.33% | 0% | 18% | -3.503% | 29.34% | 29.34% | 19% | 20.9% | 0% | 0% | 0% | 16% | 8.082% | 25.36% | 12% | 13.33% | 13.33% | 0% | 18%
| P55 | 55% | 5.623% | 29.82% | 29.82% | 24% | 26.4% | 0% | 0% | 0% | 20% | 13.55% | 27% | 19.25% | 18.38% | 18.38% | 0% | 22% | 5.623% | 29.82% | 29.82% | 24% | 26.4% | 0% | 0% | 0% | 20% | 13.55% | 27% | 19.25% | 18.38% | 18.38% | 0% | 22% | 1.903% | 29.82% | 29.82% | 24% | 26.4% | 0% | 0% | 0% | 20% | 13.55% | 27% | 19.25% | 18.38% | 18.38% | 0% | 22% | 1.903% | 29.82% | 29.82% | 24% | 26.4% | 0% | 0% | 0% | 20% | 13.55% | 27% | 19.25% | 18.38% | 18.38% | 0% | 22% | -1.816% | 29.82% | 29.82% | 24% | 26.4% | 0% | 0% | 0% | 20% | 13.55% | 27% | 19.25% | 18.38% | 18.38% | 0% | 22% | -1.816% | 29.82% | 29.82% | 24% | 26.4% | 0% | 0% | 0% | 20% | 13.55% | 27% | 19.25% | 18.38% | 18.38% | 0% | 22%
| P60 | 60% | 8.066% | 31.4% | 31.4% | 32.61% | 35.87% | 0.952% | 1.209% | 1.329% | 24% | 15.52% | 32% | 22% | 22% | 22% | 1.209% | 26% | 8.066% | 31.4% | 31.4% | 32.61% | 35.87% | 0.952% | 1.209% | 1.329% | 24% | 15.52% | 32% | 22% | 22% | 22% | 1.209% | 26% | 3.893% | 31.4% | 31.4% | 32.61% | 35.87% | 0.952% | 1.209% | 1.329% | 24% | 15.52% | 32% | 22% | 22% | 22% | 1.209% | 26% | 3.893% | 31.4% | 31.4% | 32.61% | 35.87% | 0.952% | 1.209% | 1.329% | 24% | 15.52% | 32% | 22% | 22% | 22% | 1.209% | 26% | -0.2796% | 31.4% | 31.4% | 32.61% | 35.87% | 0.952% | 1.209% | 1.329% | 24% | 15.52% | 32% | 22% | 22% | 22% | 1.209% | 26% | -0.2796% | 31.4% | 31.4% | 32.61% | 35.87% | 0.952% | 1.209% | 1.329% | 24% | 15.52% | 32% | 22% | 22% | 22% | 1.209% | 26%
| P65 | 65% | 22.01% | 57.54% | 57.54% | 51.73% | 56.9% | 19.3% | 20.38% | 22.41% | 42.57% | 31.17% | 59.94% | 38.04% | 48.43% | 48.43% | 20.38% | 45.54% | 22.01% | 57.54% | 57.54% | 51.73% | 56.9% | 19.3% | 20.38% | 22.41% | 42.57% | 31.17% | 59.94% | 38.04% | 48.43% | 48.43% | 20.38% | 45.54% | 11.41% | 44% | 44% | 38.19% | 42.01% | 5.757% | 6.836% | 7.519% | 29.03% | 17.63% | 46.4% | 24.5% | 34.89% | 34.89% | 6.836% | 32% | 11.41% | 44% | 44% | 38.19% | 42.01% | 5.757% | 6.836% | 7.519% | 29.03% | 17.63% | 46.4% | 24.5% | 34.89% | 34.89% | 6.836% | 32% | 0.8104% | 44% | 44% | 38.19% | 42.01% | 5.757% | 6.836% | 7.519% | 29.03% | 17.63% | 46.4% | 24.5% | 34.89% | 34.89% | 6.836% | 32% | 0.8104% | 44% | 44% | 38.19% | 42.01% | 5.757% | 6.836% | 7.519% | 29.03% | 17.63% | 46.4% | 24.5% | 34.89% | 34.89% | 6.836% | 32%
| P70 | 70% | 52.77% | 66.33% | 66.33% | 58.51% | 64.36% | 21.25% | 27.51% | 30.26% | 47.51% | 43.64% | 62.51% | 40.51% | 57.25% | 57.25% | 27.51% | 51.51% | 52.77% | 66.33% | 66.33% | 58.51% | 64.36% | 21.25% | 27.51% | 30.26% | 47.51% | 43.64% | 62.51% | 40.51% | 57.25% | 57.25% | 27.51% | 51.51% | 27.9% | 54.62% | 54.62% | 46.8% | 51.48% | 9.538% | 16.75% | 18.43% | 35.8% | 31.93% | 50.8% | 28.8% | 45.54% | 45.54% | 16.75% | 39.8% | 27.9% | 54.62% | 54.62% | 46.8% | 51.48% | 9.538% | 16.75% | 18.43% | 35.8% | 31.93% | 50.8% | 28.8% | 45.54% | 45.54% | 16.75% | 39.8% | 3.025% | 53.82% | 53.82% | 46% | 50.6% | 8.737% | 15% | 16.5% | 35% | 31.13% | 50% | 28% | 44.74% | 44.74% | 15% | 39% | 3.025% | 53.82% | 53.82% | 46% | 50.6% | 8.737% | 15% | 16.5% | 35% | 31.13% | 50% | 28% | 44.74% | 44.74% | 15% | 39%
| P75 | 75% | 69.84% | 108.3% | 108.3% | 98.53% | 108.4% | 56.32% | 72.81% | 80.09% | 87.88% | 80.18% | 103.9% | 76.63% | 100.9% | 100.9% | 72.81% | 92.88% | 69.84% | 108.3% | 108.3% | 98.53% | 108.4% | 56.32% | 72.81% | 80.09% | 87.88% | 80.18% | 103.9% | 76.63% | 100.9% | 100.9% | 72.81% | 92.88% | 37.74% | 75.08% | 75.08% | 65.3% | 71.83% | 23.09% | 35.46% | 39.01% | 54.65% | 46.95% | 70.65% | 43.4% | 67.65% | 67.65% | 35.46% | 59.65% | 37.74% | 75.08% | 75.08% | 65.3% | 71.83% | 23.09% | 35.46% | 39.01% | 54.65% | 46.95% | 70.65% | 43.4% | 67.65% | 67.65% | 35.46% | 59.65% | 5.646% | 64.44% | 64.44% | 54.65% | 60.11% | 12.44% | 28.93% | 31.82% | 44% | 36.3% | 60% | 32.75% | 57% | 57% | 28.93% | 49% | 5.646% | 64.44% | 64.44% | 54.65% | 60.11% | 12.44% | 28.93% | 31.82% | 44% | 36.3% | 60% | 32.75% | 57% | 57% | 28.93% | 49%
| P80 | 80% | 113.1% | 126.9% | 126.9% | 121.1% | 133.3% | 76.46% | 111.1% | 122.3% | 116.1% | 102.1% | 129.1% | 106.1% | 145.1% | 145.1% | 111.1% | 120.1% | 113.1% | 126.9% | 126.9% | 121.1% | 133.3% | 76.46% | 111.1% | 122.3% | 116.1% | 102.1% | 129.1% | 106.1% | 145.1% | 145.1% | 111.1% | 120.1% | 62.07% | 82.38% | 82.38% | 76.6% | 84.26% | 31.91% | 60.23% | 66.25% | 71.6% | 57.57% | 84.6% | 61.6% | 100.5% | 100.5% | 60.23% | 75.6% | 62.07% | 82.38% | 82.38% | 76.6% | 84.26% | 31.91% | 60.23% | 66.25% | 71.6% | 57.57% | 84.6% | 61.6% | 100.5% | 100.5% | 60.23% | 75.6% | 11.08% | 65.78% | 65.78% | 60% | 66% | 15.31% | 50% | 55% | 55% | 40.97% | 68% | 45% | 83.95% | 83.95% | 50% | 59% | 11.08% | 65.78% | 65.78% | 60% | 66% | 15.31% | 50% | 55% | 55% | 40.97% | 68% | 45% | 83.95% | 83.95% | 50% | 59%
| P85 | 85% | 120.8% | 146% | 146% | 138% | 151.8% | 80.39% | 151.6% | 166.8% | 127% | 108.6% | 135% | 129.5% | 190.2% | 190.2% | 151.6% | 134.2% | 120.8% | 146% | 146% | 138% | 151.8% | 80.39% | 151.6% | 166.8% | 127% | 108.6% | 135% | 129.5% | 190.2% | 190.2% | 151.6% | 134.2% | 72.34% | 99.93% | 99.93% | 91.93% | 101.1% | 34.32% | 107.1% | 117.8% | 80.93% | 62.49% | 88.93% | 83.43% | 144.1% | 144.1% | 107.1% | 88.09% | 72.34% | 99.93% | 99.93% | 91.93% | 101.1% | 34.32% | 107.1% | 117.8% | 80.93% | 62.49% | 88.93% | 83.43% | 144.1% | 144.1% | 107.1% | 88.09% | 23.87% | 83% | 83% | 75% | 82.5% | 17.39% | 88.63% | 97.49% | 64% | 45.56% | 72% | 66.5% | 127.2% | 127.2% | 88.63% | 71.16% | 23.87% | 83% | 83% | 75% | 82.5% | 17.39% | 88.63% | 97.49% | 64% | 45.56% | 72% | 66.5% | 127.2% | 127.2% | 88.63% | 71.16%
| P90 | 90% | 239.2% | 267.5% | 267.5% | 267.1% | 293.8% | 200.6% | 338.3% | 372.1% | 259.5% | 228.7% | 283.5% | 262.5% | 376.5% | 376.5% | 338.3% | 272.9% | 239.2% | 267.5% | 267.5% | 267.1% | 293.8% | 200.6% | 338.3% | 372.1% | 259.5% | 228.7% | 283.5% | 262.5% | 376.5% | 376.5% | 338.3% | 272.9% | 132.6% | 110.2% | 110.2% | 109.8% | 120.8% | 43.28% | 193.5% | 212.9% | 102.2% | 71.4% | 126.2% | 105.2% | 219.2% | 219.2% | 193.5% | 115.7% | 132.6% | 110.2% | 110.2% | 109.8% | 120.8% | 43.28% | 193.5% | 212.9% | 102.2% | 71.4% | 126.2% | 105.2% | 219.2% | 219.2% | 193.5% | 115.7% | 25.98% | 91% | 91% | 90.6% | 99.66% | 24.1% | 161.9% | 178% | 83% | 52.22% | 107% | 86% | 200% | 200% | 161.9% | 96.48% | 25.98% | 91% | 91% | 90.6% | 99.66% | 24.1% | 161.9% | 178% | 83% | 52.22% | 107% | 86% | 200% | 200% | 161.9% | 96.48%
| P95 | 95% | 310.4% | 271.1% | 271.1% | 319.2% | 351.1% | 209.5% | 804.8% | 885.3% | 309.4% | 246.2% | 328.2% | 295.2% | 447.6% | 447.6% | 804.8% | 341.3% | 310.4% | 271.1% | 271.1% | 319.2% | 351.1% | 209.5% | 804.8% | 885.3% | 309.4% | 246.2% | 328.2% | 295.2% | 447.6% | 447.6% | 804.8% | 341.3% | 174.6% | 113.9% | 113.9% | 161.9% | 178.1% | 52.19% | 715.1% | 786.6% | 152.1% | 88.89% | 170.9% | 137.9% | 290.4% | 290.4% | 715.1% | 184.1% | 174.6% | 113.9% | 113.9% | 161.9% | 178.1% | 52.19% | 715.1% | 786.6% | 152.1% | 88.89% | 170.9% | 137.9% | 290.4% | 290.4% | 715.1% | 184.1% | 38.86% | 94.68% | 94.68% | 142.7% | 157% | 33.01% | 628.4% | 691.2% | 132.9% | 69.71% | 151.7% | 118.8% | 271.2% | 271.2% | 628.4% | 164.9% | 38.86% | 94.68% | 94.68% | 142.7% | 157% | 33.01% | 628.4% | 691.2% | 132.9% | 69.71% | 151.7% | 118.8% | 271.2% | 271.2% | 628.4% | 164.9%
| P100 | 100%
|  |  |  | New to refurb calc: | 100%
[6 empty] | New to refurb calc: | 110%
[9 empty] | New to refurb calc: | 110%
Schedule RCF
Notes
| P0 | 0%
| P5 | 5% | NA | -7% | -7% | -37.21% | -37.21% | -7% | -27.25% | -27.25% | -35% | -16.35% | -19.7% | -19.17% | -7% | -7% | -27.25% | -35% | NA | -7% | -7% | -37.21% | -37.21% | -7% | -27.25% | -27.25% | -35% | -16.35% | -19.7% | -19.17% | -7% | -7% | -27.25% | -35% | NA | -2% | -2% | -32.21% | -32.21% | -2% | -22.25% | -22.25% | -30% | -11.35% | -14.7% | -14.17% | -2% | -2% | -22.25% | -30% | NA | -2% | -2% | -32.21% | -32.21% | -2% | -22.25% | -22.25% | -30% | -11.35% | -14.7% | -14.17% | -2% | -2% | -22.25% | -30% | NA | 0% | 0% | -30.21% | -30.21% | 0% | -20.25% | -20.25% | -28% | -9.353% | -12.7% | -12.17% | 0% | 0% | -20.25% | -28% | NA | 0% | 0% | -30.21% | -30.21% | 0% | -20.25% | -20.25% | -28% | -9.353% | -12.7% | -12.17% | 0% | 0% | -20.25% | -28%
| P10 | 10% | NA | 0% | 0% | -21.48% | -21.48% | 0% | -3.178% | -3.178% | -19% | -5.094% | -12% | -8.165% | 0% | 0% | -3.178% | -19% | NA | 0% | 0% | -21.48% | -21.48% | 0% | -3.178% | -3.178% | -19% | -5.094% | -12% | -8.165% | 0% | 0% | -3.178% | -19% | NA | 0% | 0% | -21.48% | -21.48% | 0% | -3.178% | -3.178% | -19% | -5.094% | -12% | -8.165% | 0% | 0% | -3.178% | -19% | NA | 0% | 0% | -21.48% | -21.48% | 0% | -3.178% | -3.178% | -19% | -5.094% | -12% | -8.165% | 0% | 0% | -3.178% | -19% | NA | 0% | 0% | -21.48% | -21.48% | 0% | -3.178% | -3.178% | -19% | -5.094% | -12% | -8.165% | 0% | 0% | -3.178% | -19% | NA | 0% | 0% | -21.48% | -21.48% | 0% | -3.178% | -3.178% | -19% | -5.094% | -12% | -8.165% | 0% | 0% | -3.178% | -19%
| P15 | 15% | NA | 0% | 0% | -13% | -13% | 0% | 0% | 0% | -11.91% | -1.219% | -5.397% | -0.6793% | 0% | 0% | 0% | -11.91% | NA | 0% | 0% | -13% | -13% | 0% | 0% | 0% | -11.91% | -1.219% | -5.397% | -0.6793% | 0% | 0% | 0% | -11.91% | NA | 0% | 0% | -13% | -13% | 0% | 0% | 0% | -11.91% | -1.219% | -5.397% | -0.6793% | 0% | 0% | 0% | -11.91% | NA | 0% | 0% | -13% | -13% | 0% | 0% | 0% | -11.91% | -1.219% | -5.397% | -0.6793% | 0% | 0% | 0% | -11.91% | NA | 0% | 0% | -13% | -13% | 0% | 0% | 0% | -11.91% | -1.219% | -5.397% | -0.6793% | 0% | 0% | 0% | -11.91% | NA | 0% | 0% | -13% | -13% | 0% | 0% | 0% | -11.91% | -1.219% | -5.397% | -0.6793% | 0% | 0% | 0% | -11.91%
| P20 | 20% | NA | 0% | 0% | -8.582% | -8.582% | 0% | 0% | 0% | -6% | 3.171% | -4.14% | 0% | 0% | 0% | 0% | -6% | NA | 0% | 0% | -8.582% | -8.582% | 0% | 0% | 0% | -6% | 3.171% | -4.14% | 0% | 0% | 0% | 0% | -6% | NA | 0% | 0% | -8.582% | -8.582% | 0% | 0% | 0% | -6% | 3.171% | -4.14% | 0% | 0% | 0% | 0% | -6% | NA | 0% | 0% | -8.582% | -8.582% | 0% | 0% | 0% | -6% | 3.171% | -4.14% | 0% | 0% | 0% | 0% | -6% | NA | 0% | 0% | -8.582% | -8.582% | 0% | 0% | 0% | -6% | 3.171% | -4.14% | 0% | 0% | 0% | 0% | -6% | NA | 0% | 0% | -8.582% | -8.582% | 0% | 0% | 0% | -6% | 3.171% | -4.14% | 0% | 0% | 0% | 0% | -6%
| P25 | 25% | NA | -3% | -3% | -4.57% | -4.57% | -3% | -3% | -3% | -4.443% | 4.738% | -7% | -3% | -3% | -3% | -3% | -4.443% | NA | -3% | -3% | -4.57% | -4.57% | -3% | -3% | -3% | -4.443% | 4.738% | -7% | -3% | -3% | -3% | -3% | -4.443% | NA | -3% | -3% | -4.57% | -4.57% | -3% | -3% | -3% | -4.443% | 4.738% | -7% | -3% | -3% | -3% | -3% | -4.443% | NA | -3% | -3% | -4.57% | -4.57% | -3% | -3% | -3% | -4.443% | 4.738% | -7% | -3% | -3% | -3% | -3% | -4.443% | NA | 0% | 0% | -1.57% | -1.57% | 0% | 0% | 0% | -1.443% | 7.738% | -4% | 0% | 0% | 0% | 0% | -1.443% | NA | 0% | 0% | -1.57% | -1.57% | 0% | 0% | 0% | -1.443% | 7.738% | -4% | 0% | 0% | 0% | 0% | -1.443%
| P30 | 30% | NA | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 13.31% | -1.6% | 0% | 0% | 0% | 0% | 0% | NA | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 13.31% | -1.6% | 0% | 0% | 0% | 0% | 0% | NA | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 13.31% | -1.6% | 0% | 0% | 0% | 0% | 0% | NA | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 13.31% | -1.6% | 0% | 0% | 0% | 0% | 0% | NA | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 13.31% | -1.6% | 0% | 0% | 0% | 0% | 0% | NA | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 13.31% | -1.6% | 0% | 0% | 0% | 0% | 0%
| P35 | 35% | NA | 12.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 20.41% | 0% | 2.09% | 0% | 0% | 0% | 0% | NA | 12.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 20.41% | 0% | 2.09% | 0% | 0% | 0% | 0% | NA | 12.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 20.41% | 0% | 2.09% | 0% | 0% | 0% | 0% | NA | 12.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 20.41% | 0% | 2.09% | 0% | 0% | 0% | 0% | NA | 12.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 20.41% | 0% | 2.09% | 0% | 0% | 0% | 0% | NA | 12.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 20.41% | 0% | 2.09% | 0% | 0% | 0% | 0%
| P40 | 40% | NA | 12.33% | 12.33% | 6.861% | 6.861% | -1% | -1% | -1% | -0.6427% | 20.33% | -1% | 2.339% | -1% | -1% | -1% | -0.6427% | NA | 12.33% | 12.33% | 6.861% | 6.861% | -1% | -1% | -1% | -0.6427% | 20.33% | -1% | 2.339% | -1% | -1% | -1% | -0.6427% | NA | 12.33% | 12.33% | 6.861% | 6.861% | -1% | -1% | -1% | -0.6427% | 20.33% | -1% | 2.339% | -1% | -1% | -1% | -0.6427% | NA | 12.33% | 12.33% | 6.861% | 6.861% | -1% | -1% | -1% | -0.6427% | 20.33% | -1% | 2.339% | -1% | -1% | -1% | -0.6427% | NA | 13.33% | 13.33% | 7.861% | 7.861% | 0% | 0% | 0% | 0.3573% | 21.33% | 0% | 3.339% | 0% | 0% | 0% | 0.3573% | NA | 13.33% | 13.33% | 7.861% | 7.861% | 0% | 0% | 0% | 0.3573% | 21.33% | 0% | 3.339% | 0% | 0% | 0% | 0.3573%
| P45 | 45% | NA | 16.67% | 16.67% | 15.8% | 15.8% | 0% | 0% | 0% | 6.013% | 23.02% | 0.7% | 4.7% | 0.9632% | 0.9632% | 0% | 6.013% | NA | 16.67% | 16.67% | 15.8% | 15.8% | 0% | 0% | 0% | 6.013% | 23.02% | 0.7% | 4.7% | 0.9632% | 0.9632% | 0% | 6.013% | NA | 16.67% | 16.67% | 15.8% | 15.8% | 0% | 0% | 0% | 6.013% | 23.02% | 0.7% | 4.7% | 0.9632% | 0.9632% | 0% | 6.013% | NA | 16.67% | 16.67% | 15.8% | 15.8% | 0% | 0% | 0% | 6.013% | 23.02% | 0.7% | 4.7% | 0.9632% | 0.9632% | 0% | 6.013% | NA | 16.67% | 16.67% | 15.8% | 15.8% | 0% | 0% | 0% | 6.013% | 23.02% | 0.7% | 4.7% | 0.9632% | 0.9632% | 0% | 6.013% | NA | 16.67% | 16.67% | 15.8% | 15.8% | 0% | 0% | 0% | 6.013% | 23.02% | 0.7% | 4.7% | 0.9632% | 0.9632% | 0% | 6.013%
| P50 | 50% | NA | 18.33% | 18.33% | 20% | 20% | 0% | 0% | 0% | 12.27% | 27.69% | 1.316% | 15% | 4.692% | 4.692% | 0% | 12.27% | NA | 18.33% | 18.33% | 20% | 20% | 0% | 0% | 0% | 12.27% | 27.69% | 1.316% | 15% | 4.692% | 4.692% | 0% | 12.27% | NA | 18.33% | 18.33% | 20% | 20% | 0% | 0% | 0% | 12.27% | 27.69% | 1.316% | 15% | 4.692% | 4.692% | 0% | 12.27% | NA | 18.33% | 18.33% | 20% | 20% | 0% | 0% | 0% | 12.27% | 27.69% | 1.316% | 15% | 4.692% | 4.692% | 0% | 12.27% | NA | 18.33% | 18.33% | 20% | 20% | 0% | 0% | 0% | 12.27% | 27.69% | 1.316% | 15% | 4.692% | 4.692% | 0% | 12.27% | NA | 18.33% | 18.33% | 20% | 20% | 0% | 0% | 0% | 12.27% | 27.69% | 1.316% | 15% | 4.692% | 4.692% | 0% | 12.27%
| P55 | 55% | NA | 39.5% | 39.5% | 28.6% | 28.6% | 0% | 7.436% | 7.436% | 16% | 32.43% | 3.2% | 16.82% | 14.05% | 14.05% | 7.436% | 16% | NA | 39.5% | 39.5% | 28.6% | 28.6% | 0% | 7.436% | 7.436% | 16% | 32.43% | 3.2% | 16.82% | 14.05% | 14.05% | 7.436% | 16% | NA | 39.5% | 39.5% | 28.6% | 28.6% | 0% | 7.436% | 7.436% | 16% | 32.43% | 3.2% | 16.82% | 14.05% | 14.05% | 7.436% | 16% | NA | 39.5% | 39.5% | 28.6% | 28.6% | 0% | 7.436% | 7.436% | 16% | 32.43% | 3.2% | 16.82% | 14.05% | 14.05% | 7.436% | 16% | NA | 39.5% | 39.5% | 28.6% | 28.6% | 0% | 7.436% | 7.436% | 16% | 32.43% | 3.2% | 16.82% | 14.05% | 14.05% | 7.436% | 16% | NA | 39.5% | 39.5% | 28.6% | 28.6% | 0% | 7.436% | 7.436% | 16% | 32.43% | 3.2% | 16.82% | 14.05% | 14.05% | 7.436% | 16%
| P60 | 60% | NA | 50% | 50% | 32.6% | 32.6% | 0% | 14.67% | 14.67% | 21.87% | 42.41% | 8.806% | 20.7% | 18.57% | 18.57% | 14.67% | 21.87% | NA | 50% | 50% | 32.6% | 32.6% | 0% | 14.67% | 14.67% | 21.87% | 42.41% | 8.806% | 20.7% | 18.57% | 18.57% | 14.67% | 21.87% | NA | 50% | 50% | 32.6% | 32.6% | 0% | 14.67% | 14.67% | 21.87% | 42.41% | 8.806% | 20.7% | 18.57% | 18.57% | 14.67% | 21.87% | NA | 50% | 50% | 32.6% | 32.6% | 0% | 14.67% | 14.67% | 21.87% | 42.41% | 8.806% | 20.7% | 18.57% | 18.57% | 14.67% | 21.87% | NA | 50% | 50% | 32.6% | 32.6% | 0% | 14.67% | 14.67% | 21.87% | 42.41% | 8.806% | 20.7% | 18.57% | 18.57% | 14.67% | 21.87% | NA | 50% | 50% | 32.6% | 32.6% | 0% | 14.67% | 14.67% | 21.87% | 42.41% | 8.806% | 20.7% | 18.57% | 18.57% | 14.67% | 21.87%
| P65 | 65% | NA | 50% | 50% | 40% | 40% | 0% | 23.18% | 23.18% | 27% | 47.33% | 10.85% | 22% | 29.81% | 29.81% | 23.18% | 27% | NA | 50% | 50% | 40% | 40% | 0% | 23.18% | 23.18% | 27% | 47.33% | 10.85% | 22% | 29.81% | 29.81% | 23.18% | 27% | NA | 50% | 50% | 40% | 40% | 0% | 23.18% | 23.18% | 27% | 47.33% | 10.85% | 22% | 29.81% | 29.81% | 23.18% | 27% | NA | 50% | 50% | 40% | 40% | 0% | 23.18% | 23.18% | 27% | 47.33% | 10.85% | 22% | 29.81% | 29.81% | 23.18% | 27% | NA | 50% | 50% | 40% | 40% | 0% | 23.18% | 23.18% | 27% | 47.33% | 10.85% | 22% | 29.81% | 29.81% | 23.18% | 27% | NA | 50% | 50% | 40% | 40% | 0% | 23.18% | 23.18% | 27% | 47.33% | 10.85% | 22% | 29.81% | 29.81% | 23.18% | 27%
| P70 | 70% | NA | 53% | 53% | 45.92% | 45.92% | 3% | 34.29% | 34.29% | 38.97% | 53.84% | 15.8% | 36.4% | 50.61% | 50.61% | 34.29% | 38.97% | NA | 53% | 53% | 45.92% | 45.92% | 3% | 34.29% | 34.29% | 38.97% | 53.84% | 15.8% | 36.4% | 50.61% | 50.61% | 34.29% | 38.97% | NA | 58% | 58% | 50.92% | 50.92% | 8% | 39.29% | 39.29% | 43.97% | 58.84% | 20.8% | 41.4% | 55.61% | 55.61% | 39.29% | 43.97% | NA | 58% | 58% | 50.92% | 50.92% | 8% | 39.29% | 39.29% | 43.97% | 58.84% | 20.8% | 41.4% | 55.61% | 55.61% | 39.29% | 43.97% | NA | 50% | 50% | 42.92% | 42.92% | 0% | 31.29% | 31.29% | 35.97% | 50.84% | 12.8% | 33.4% | 47.61% | 47.61% | 31.29% | 35.97% | NA | 50% | 50% | 42.92% | 42.92% | 0% | 31.29% | 31.29% | 35.97% | 50.84% | 12.8% | 33.4% | 47.61% | 47.61% | 31.29% | 35.97%
| P75 | 75% | NA | 58% | 58% | 58% | 58% | 8% | 52.96% | 52.96% | 53.71% | 70.37% | 34% | 43% | 65.5% | 65.5% | 52.96% | 53.71% | NA | 58% | 58% | 58% | 58% | 8% | 52.96% | 52.96% | 53.71% | 70.37% | 34% | 43% | 65.5% | 65.5% | 52.96% | 53.71% | NA | 63% | 63% | 63% | 63% | 13% | 57.96% | 57.96% | 58.71% | 75.37% | 39% | 48% | 70.5% | 70.5% | 57.96% | 58.71% | NA | 63% | 63% | 63% | 63% | 13% | 57.96% | 57.96% | 58.71% | 75.37% | 39% | 48% | 70.5% | 70.5% | 57.96% | 58.71% | NA | 50% | 50% | 50% | 50% | 0% | 44.96% | 44.96% | 45.71% | 62.37% | 26% | 35% | 57.5% | 57.5% | 44.96% | 45.71% | NA | 50% | 50% | 50% | 50% | 0% | 44.96% | 44.96% | 45.71% | 62.37% | 26% | 35% | 57.5% | 57.5% | 44.96% | 45.71%
| P80 | 80% | NA | 70.57% | 70.57% | 73% | 73% | 12% | 70.3% | 70.3% | 71.4% | 75.82% | 54.34% | 49.4% | 79.8% | 79.8% | 70.3% | 71.4% | NA | 70.57% | 70.57% | 73% | 73% | 12% | 70.3% | 70.3% | 71.4% | 75.82% | 54.34% | 49.4% | 79.8% | 79.8% | 70.3% | 71.4% | NA | 75.57% | 75.57% | 78% | 78% | 17% | 75.3% | 75.3% | 76.4% | 80.82% | 59.34% | 54.4% | 84.8% | 84.8% | 75.3% | 76.4% | NA | 75.57% | 75.57% | 78% | 78% | 17% | 75.3% | 75.3% | 76.4% | 80.82% | 59.34% | 54.4% | 84.8% | 84.8% | 75.3% | 76.4% | NA | 58.57% | 58.57% | 61% | 61% | 0% | 58.3% | 58.3% | 59.4% | 63.82% | 42.34% | 37.4% | 67.8% | 67.8% | 58.3% | 59.4% | NA | 58.57% | 58.57% | 61% | 61% | 0% | 58.3% | 58.3% | 59.4% | 63.82% | 42.34% | 37.4% | 67.8% | 67.8% | 58.3% | 59.4%
| P85 | 85% | NA | 95.03% | 95.03% | 92.4% | 92.4% | 14% | 97.33% | 97.33% | 89% | 77.95% | 81.8% | 59% | 114% | 114% | 97.33% | 89% | NA | 95.03% | 95.03% | 92.4% | 92.4% | 14% | 97.33% | 97.33% | 89% | 77.95% | 81.8% | 59% | 114% | 114% | 97.33% | 89% | NA | 95.03% | 95.03% | 92.4% | 92.4% | 14% | 97.33% | 97.33% | 89% | 77.95% | 81.8% | 59% | 114% | 114% | 97.33% | 89% | NA | 95.03% | 95.03% | 92.4% | 92.4% | 14% | 97.33% | 97.33% | 89% | 77.95% | 81.8% | 59% | 114% | 114% | 97.33% | 89% | NA | 81.03% | 81.03% | 78.4% | 78.4% | 0% | 83.33% | 83.33% | 75% | 63.95% | 67.8% | 45% | 100% | 100% | 83.33% | 75% | NA | 81.03% | 81.03% | 78.4% | 78.4% | 0% | 83.33% | 83.33% | 75% | 63.95% | 67.8% | 45% | 100% | 100% | 83.33% | 75%
| P90 | 90% | NA | 108.9% | 108.9% | 131.2% | 131.2% | 32.32% | 137.2% | 137.2% | 120% | 84.7% | 98.45% | 82.8% | 153.3% | 153.3% | 137.2% | 120% | NA | 108.9% | 108.9% | 131.2% | 131.2% | 32.32% | 137.2% | 137.2% | 120% | 84.7% | 98.45% | 82.8% | 153.3% | 153.3% | 137.2% | 120% | NA | 113.9% | 113.9% | 136.2% | 136.2% | 37.32% | 142.2% | 142.2% | 125% | 89.7% | 103.5% | 87.8% | 158.3% | 158.3% | 142.2% | 125% | NA | 113.9% | 113.9% | 136.2% | 136.2% | 37.32% | 142.2% | 142.2% | 125% | 89.7% | 103.5% | 87.8% | 158.3% | 158.3% | 142.2% | 125% | NA | 88.89% | 88.89% | 111.2% | 111.2% | 12.32% | 117.2% | 117.2% | 100% | 64.7% | 78.45% | 62.8% | 133.3% | 133.3% | 117.2% | 100% | NA | 88.89% | 88.89% | 111.2% | 111.2% | 12.32% | 117.2% | 117.2% | 100% | 64.7% | 78.45% | 62.8% | 133.3% | 133.3% | 117.2% | 100%
| P95 | 95% | NA | 103.9% | 103.9% | 153% | 153% | 58.32% | 211.6% | 211.6% | 161.1% | 94.27% | 100.3% | 98% | 185.6% | 185.6% | 211.6% | 161.1% | NA | 103.9% | 103.9% | 153% | 153% | 58.32% | 211.6% | 211.6% | 161.1% | 94.27% | 100.3% | 98% | 185.6% | 185.6% | 211.6% | 161.1% | NA | 118.9% | 118.9% | 168% | 168% | 73.32% | 226.6% | 226.6% | 176.1% | 109.3% | 115.3% | 113% | 200.6% | 200.6% | 226.6% | 176.1% | NA | 118.9% | 118.9% | 168% | 168% | 73.32% | 226.6% | 226.6% | 176.1% | 109.3% | 115.3% | 113% | 200.6% | 200.6% | 226.6% | 176.1% | NA | 88.89% | 88.89% | 138% | 138% | 43.32% | 196.6% | 196.6% | 146.1% | 79.27% | 85.29% | 83% | 170.6% | 170.6% | 196.6% | 146.1% | NA | 88.89% | 88.89% | 138% | 138% | 43.32% | 196.6% | 196.6% | 146.1% | 79.27% | 85.29% | 83% | 170.6% | 170.6% | 196.6% | 146.1%
| P100 | 100%

## Selectors (hidden)
GRIP Stages | HMT Stage | Size | Options
GRIP ≤2 | SOBC | >£1Bn | SOBC>£1Bn
GRIP 3 | OBC | <=£1Bn | SOBC<=£1Bn
GRIP 4 | FBC |  | OBC>£1Bn | ??<=£1Bn
OBC<=£1Bn
FBC>£1Bn
FBC<=£1Bn